## Slide 1
WEEKLY SYSTEMS DEVELOPMENT UPDATE
Vessel Operations,
Tracking & AIS Readiness
Progress report covering voyage-route enhancements, role-based vessel access, AIS integration coordination, and testing deployment.
REPORTING PERIOD
October 12â€“16, 2026
Prepared by: IT Department

## Slide 2
EXECUTIVE SUMMARY
This week at a glance
Four workstreams moved forward, with the AIS connection dependent on provider activation.
Voyage Routing
ENHANCED
Auto-generated and manual route options improved, including editable route points.
Vessel Access
DEPLOYED
Operations Manager and vessel-specific Operation Manager access are now separated.
AIS Integration
AWAITING PROVIDER
Kpler/MarineTraffic account and requirements submitted; commercial activation pending.
System Testing
READY
Testing release deployed and verified with targeted automated test coverage.
Overall status
Core system improvements are deployed for testing; external AIS activation remains the primary dependency.
VILLA GROUP OF COMPANIES â€¢ INTERNAL MANAGEMENT UPDATE
02

## Slide 3
VOYAGE TRACKING
Improved route planning and actual-track visibility
The planned route remains available while actual vessel updates create a distinct operational track.
01
Plan
Generate a suggested route or draw a manual route on the map.
02
Track
Recorded vessel positions create a separate traveled line.
03
Complete
Connect the latest position to the remaining planned route and destination.
ROUTE VISUALIZATION
Planned route
Actual traveled track
Key benefit
Deviations remain visible without losing the approved plan.
VILLA GROUP OF COMPANIES â€¢ INTERNAL MANAGEMENT UPDATE
03

## Slide 4
USER MANAGEMENT
Clear management scope by vessel responsibility
Access now follows the operating structure of Marine Operations.
OPERATIONS MANAGER
OPERATION MANAGER
Company-wide management scope
Vessel-specific management scope
â€¢ Access to all vessels
â€¢ No vessel assignment required
â€¢ Company-wide operational oversight
â€¢ Full Marine Operations visibility
â€¢ Vessel Assignment is required
â€¢ Access limited to assigned vessels
â€¢ Manager actions within assigned vessels
â€¢ Vessel-specific checklist reminders
Result: stronger data separation, clearer accountability, and access aligned with vessel assignments.
VILLA GROUP OF COMPANIES â€¢ INTERNAL MANAGEMENT UPDATE
04

## Slide 5
AIS INTEGRATION
Kpler / MarineTraffic coordination status
The system design is ready to consume live vessel positions once commercial API access is activated.
Onboard AIS
Xinuo Class B
AIS Network
Receiver coverage
Kpler API
Activation pending
VSLI System
Live monitoring map
COMPLETED
Developer account created â€¢ API credential generated â€¢ requirements and vessel-monitoring use case submitted
PENDING EXTERNAL ACTION
Provider activation, coverage confirmation, commercial terms, and pricing proposal from Kpler/MarineTraffic
VILLA GROUP OF COMPANIES â€¢ INTERNAL MANAGEMENT UPDATE
05

## Slide 6
DEPLOYMENT & QUALITY
Current release deployed for system testing
The live environment is being used for controlled validation before final operational acceptance.
TESTING RELEASE DEPLOYED
Available for user validation and workflow confirmation
DEPLOYED
43
Targeted tests passed
374
Assertions passed
0
New tables or columns
100%
Selected test success
Validation completed
Vessel access restrictions â€¢ Calendar permissions â€¢ Organization access â€¢ User management
VILLA GROUP OF COMPANIES â€¢ INTERNAL MANAGEMENT UPDATE
06

## Slide 7
NEXT STEPS
Priorities for the next work cycle
Focus shifts to live-user validation and the external AIS decision.
01
Monitor the testing deployment
Collect user feedback and confirm the Operation Manager vessel-assignment workflow.
02
Follow up with Kpler / MarineTraffic
Secure API activation, vessel coverage confirmation, technical terms, and pricing.
03
Prepare AIS server integration
Implement secure server-side synchronization and MMSI/IMO vessel matching after approval.
04
Complete operational acceptance
Validate live map accuracy, route behavior, and user permissions before final sign-off.
END OF UPDATE
VILLA GROUP OF COMPANIES â€¢ INTERNAL MANAGEMENT UPDATE
07